AI HOLDING COMPANY

Sharpened Project Plan  ·  v5

Owner: J (CEO)  ·  Date: 2026-04-13  ·  100% local · Ollama / python-telegram-bot / CrewAI

fig. 01  ·  Operating Model v5  ·  AI Holding Company

What Changed in v5

Version 5 promotes the system from an AI operations/reporting layer into an AI business-management layer. Key changes:

| Area | v4 | v5 |
| --- | --- | --- |
| Company name | AI Capital Group | AI Holding Company |
| Treasury Division | Ledger, P&L, risk alerts | Replaced by Commercial Division — full business-management mandate (feasibility, ROI, scoring, scenario modelling, post-launch review) |
| Content Studio | Not in plan | Stage J — brief-driven, light, after Stage D green |
| Marketing Division | Not in plan | Stage K — gated (G1): only after A, B, D stable and green; 1 campaign/week max |
| Guardrails | None formal | G1–G7: Sequence, Load, Decision, Publishing, KPI, Silence, Complexity stop-rule |
| Board Pack | 4 fields | 8 required fields — Rationale, Upside, Effort, Confidence, Owner, Deadline, Dissent, Post-launch measurement |
| Commercial scoring gate | Not required | Mandatory: Commercial must score every new initiative before Board Pack or Stage 03 |
| Stage count | Stages A–I | Stages A–K (+ optional F) |

System Vision

AI Holding Company is a fully local AI-powered business-management layer that sits on top of existing operations without modifying their core logic.

It manages two trading bots (Forex/MT5 on desktop, Polymarket on VPS), two websites (Trading Tools, Productivity Tools / FreeTraderHub), and a growing set of AI divisions. The system saves CEO time, raises decision quality, and surfaces the right information at the right moment — while J retains full strategic authority.

Strategic Shift (v5)

The system is no longer just an operations/reporting layer. It is evolving into an AI business-management layer. This means the system does not only monitor and report — it assesses feasibility, scores initiatives, estimates ROI, and surfaces the right decisions at the right time. The CEO decides. Divisions plan and execute. The Managing Agent coordinates, QAs, and filters.

Non-Negotiable Rules (R1–R10)

These rules cannot be overridden by any agent, plan, or tool. The Compliance Guardian vets every approved plan against R1–R11 before Stage 04 fires.

| # | Rule | Detail |
| --- | --- | --- |
| R1 | 100% local | All inference via Ollama only. No cloud APIs. No OpenAI, Anthropic Claude API, Grok, Gemini, or equivalent. |
| R2 | Bots stay untouched | MT5 and Polymarket bot source is read-only. No writes, no deploys, no parameter changes without explicit CEO approval via the Loop. |
| R3 | Website source protected | Website source is read-only for all agents except the Developer Tool, and only after CEO approval via the Loop. |
| R4 | No auto-publish of AI prose | Deterministic data may auto-publish after plan approval. AI-generated prose requires CEO review. All external content and website changes escalate under R4 and R3. |
| R5 | No live money without CEO | Fund movement, trade execution, cost commitment >$50, drawdown response — all require CEO approval. |
| R6 | Compliance Guardian always runs | Vets every approved plan against R1–R10 before Stage 04 fires. Cannot be disabled. |
| R7 | MA copied on all comms | If CEO communicates directly with a divisional head, the Managing Agent is always copied. |
| R8 | Developer Tool scope gate | qwen2.5-coder:7b writes only to files inside ai-capital-group/. Never to bot source, website source, or any file outside this folder. |
| R9 | Two net-negative weeks = halt | If Time Saved sheet shows net-negative CEO hours for two consecutive weeks, all new work halts. Review the operating model before adding anything. |
| R10 | Silence by default | No unsolicited messages unless: (a) decision pending for CEO, (b) status colour changed, or (c) seven days passed with no communication. |
| R11 | No OpenClaw — python-telegram-bot only | OpenClaw is prohibited. Telegram gateway must use python-telegram-bot (direct Bot API polling, pure Python, no Docker, no broker). BOT_TOKEN stored in local .env only, never transmitted to a third-party service. Compliance Guardian blocks any plan introducing OpenClaw or a Docker-based Telegram gateway. |

The Operating Model — Six-Stage Loop

Every piece of work runs through this loop. No exceptions. The Compliance Guardian cross-checks every plan at Stage 03 before Stage 04 fires.

| Stage | Name | Who acts | What happens |
| --- | --- | --- | --- |
| 01 | GOAL | CEO | Issues the goal in plain English via Telegram. The NLU layer (llama3.2:3b) parses it into a structured Goal object and routes it to the MA. |
| 02 | PLAN | Division | The relevant Division proposes how it will achieve the goal: steps, models, tools, time estimate, success criteria. Commercial must score any new initiative before this plan can proceed. |
| 03 | APPROVE | MA or CEO | MA checks the plan against R1–R10 and G1–G7. Compliance Guardian runs. If clear, MA approves routine work. If a fixed escalation rule triggers, MA escalates to CEO. |
| 04 | EXECUTE | Division | Division runs the approved plan. Developer Tool (qwen2.5-coder:7b) may be invoked for scripting. CEO reviews any code diff before deploy. |
| 05 | REPORT | Division → MA QA | Division files the report. MA runs QA against the original success criteria. If pass, report goes to CEO. If fail, MA re-tasks the Division. |
| 06 | JUDGE | CEO | CEO reviews the report and either accepts (loop closes) or re-tasks the Division with new guidance. The goal only closes when the CEO accepts. |

Standing Rules

- Decision Queue hard-capped at 5 open items. A sixth waits.

- System is silent by default (R10). The MA does not speak unless triggered.

- Two consecutive net-negative weeks halts all new division rollout (R9, G7).

- Commercial must score any new initiative before it reaches the Board Pack (new in v5).

Managing Agent — Role, Authority & Escalation

The Managing Agent (MA) is the operational decision-maker between the CEO and the divisions. It operates like a Chief of Staff / COO — coordinating work, quality-checking outputs, and filtering noise before it reaches the CEO. Model: llama3.1:8b.

Always Escalates to CEO

| # | Trigger | Detail | Ref |
| --- | --- | --- | --- |
| 1 | Live money / cost >$50 | Fund movement, trade execution, drawdown response, any cost commitment above $50 | R5 |
| 2 | Code deployment | Any write to bot source, website source, or system scripts | R8 |
| 3 | External publishing | Any content going live on public-facing websites or social | R4 |
| 4 | New plan type | First time a division proposes a plan of this type — pattern not in ruleset | §5 |
| 5 | Compliance Guardian flagged | Guardian raised a rule violation on this plan | R6 |
| 6 | Goal overrun | Goal running >2× its estimated effort without completion | §5 |
| 7 | Inter-division conflict | MA cannot resolve a conflict between divisions in one cycle | §5 |
| 8 | MA uncertain | Decision cannot be classified against the ruleset — MA explains why | §5 |
| 9 | KPI fields missing | Any new initiative without all 5 KPI fields (owner, upside, effort/cost, KPI/metric, review date) | §8 |

MA Handles Without CEO

| # | Decision type | Examples | Ref |
| --- | --- | --- | --- |
| 1 | Routine monitoring approvals | Read bot logs, check website uptime, generate daily brief | §5 |
| 2 | Intra-division operational decisions | How to structure a report, which fields to include | §5 |
| 3 | Progress chasing | Reminding a division a task is overdue within approved scope | §5 |
| 4 | QA verification | Checking completed work against original success criteria before reporting up | §5 |
| 5 | Scheduling and ordering | Which tasks run first within an approved plan | §5 |
| 6 | Copying CEO comms | When CEO messages a division directly, MA is copied and acknowledges | R7 |

Escalation Message Format

[ESCALATION] Cannot classify: <one-line explanation>.
Options: <A>, <B>.
Recommendation: <X>.

CEO replies. MA logs and acts. MA never guesses on an edge case.

Guardrails (G1–G7) — Complexity Creep Prevention

These guardrails apply to all new division rollouts and initiatives. They exist to prevent the system from growing faster than it can prove value.

| Code | Name | Rule |
| --- | --- | --- |
| G1 | Sequence guard | Do not add new outward-facing divisions until Stage A, B, and D are stable and green. |
| G2 | Load guard | Do not activate more than one new division at a time. Each must prove value against explicit success criteria before the next activates. |
| G3 | Decision guard | Marketing: max 1 campaign decision/week. Content: operates from approved briefs only — no open-ended work. Commercial: must score any new initiative before it reaches the Board Pack. |
| G4 | Publishing guard | Content may draft assets. All public publishing, website changes, or external content releases escalate under R3 and R4. No exceptions. |
| G5 | KPI guard | No new initiative enters execution without: named owner, expected upside, expected effort/cost, KPI or success metric, review date, post-launch measurement plan. |
| G6 | Silence guard | New divisions obey R10. They surface only: pending decisions, colour/status changes, and explicitly allowed digest outputs. |
| G7 | Complexity stop-rule | If two consecutive weeks show net-negative time saved (R9), pause all new division rollout and review the operating model before adding anything. |

Board Pack Requirements (v5)

Every proposed decision in the weekly Board Pack must include all eight fields. The MA blocks any decision missing a field from reaching the CEO. Commercial must score any new initiative (upside, effort, confidence, go/no-go) before it reaches the Board Pack — unscored initiatives are blocked by MA.

| # | Field | Required content |
| --- | --- | --- |
| 1 | Rationale | Why this decision / initiative is being proposed now |
| 2 | Expected upside | Quantified where possible — revenue, time saved, risk reduced |
| 3 | Expected effort / cost | Time, compute, money — realistic estimate |
| 4 | Confidence level | High / Medium / Low with a one-line reason |
| 5 | Owner | Named division or agent responsible for execution |
| 6 | Deadline / review date | Hard date for completion or first review |
| 7 | Dissent / counter-argument | Dissent agent must file one objection minimum |
| 8 | Post-launch measurement plan | How success will be measured after execution |

Commercial Division Charter (replaces Treasury)

Commercial owns the business-management function. Finance Reporting and Risk Monitoring are sub-functions inside Commercial, not the whole division. Commercial is the gate-keeper: no new initiative enters execution without a Commercial score.

Commercial answers four questions

- Should we do this? — feasibility assessment

- What is the expected payoff? — ROI projection

- What does success look like numerically? — KPI definition

- Was it worth it afterward? — post-launch review vs forecast

Sub-functions

| Sub-function | Scope |
| --- | --- |
| Finance Reporting | Daily PNL roll-up, weekly P&L statement |
| Business Case / Feasibility | Go/no-go assessment for new initiatives |
| ROI & Impact | Projection, scoring, prioritisation, scenario modelling |
| Risk Monitoring | Drawdown alerts, cost spike detection, exposure flags |

Model: llama3.1:8b for analysis. Python tools for all arithmetic — no LLM arithmetic.

Organisation Structure

Near-term org (next 8 weeks)

| Division | Status | Notes |
| --- | --- | --- |
| Trading | LIVE (AMBER) | Polymarket recency stale — Stage D fixes |
| Websites | LIVE (RED) | Research brief freshness — Stage D fixes |
| Research | PLANNED (Stage E) | On-demand first, weekly opt-in later |
| Commercial | PLANNED (Stage G) | Replaces Treasury. Full business-management mandate. |
| Content Studio | PLANNED (Stage J) | Add after Stage D green. Light first — inside Websites or standalone. |
| Marketing | PLANNED (Stage K) | Only after A, B, D stable and green. 1 campaign decision/week max. |
| Ideas | OPTIONAL | Reconsider once Commercial + Marketing exist. |

Model Architecture

All inference local via Ollama. Zero cloud APIs. This is non-negotiable per R1.

| Model | Tag | Role | Notes |
| --- | --- | --- | --- |
| Llama 3.1 8B | llama3.1:8b | MA / CEO Layer / Division Managers | Primary reasoning. MA coordination, Commercial analysis, Board Pack synthesis. |
| Llama 3.2 3B | llama3.2:latest | Telegram Router / NLU Intake | Fast intent parser. Translates plain-English CEO messages into structured Goals. |
| Qwen2.5 Coder 7B | qwen2.5-coder:7b | Developer Tool (Stage I) | ai-capital-group/ scope only. CEO reviews diff before deploy. |
| nomic-embed-text | nomic-embed-text:latest | Semantic Memory (Stage I+) | Embedding only. Not generative. Future semantic search. |

Stage Plan — A through K

Critical path: A → B → D → G → H → J → I  |  Parallel: C alongside A/B  |  Gated: K only after A, B, D green  |  Optional: F

| Stage | Title | Status | Priority | Guardrails |
| --- | --- | --- | --- | --- |
| A | Telegram + NLU + MA + Compliance Guardian + Silence | 🔴 NOT STARTED | P0 | — |
| B | Scheduler Verification & Self-Heal | 🔴 NOT STARTED | P0 | — |
| C | Sanitizer & Allowlist Remediation | 🔴 NOT STARTED | P1 (parallel) | — |
| D | Operational Signals → GREEN | 🔴 NOT STARTED | P1 | Unblock G1 |
| G | Commercial Division | 🔴 NOT STARTED | P1 | G2: one at a time |
| E | Research Division (on-demand first) | 🔴 NOT STARTED | P2 | G2 |
| H | Holding Board v2 + Board Pack upgrade | 🔴 NOT STARTED | P2 | — |
| J | Content Studio (light) | 🔴 NOT STARTED | P2 | G1, G2, G3, G4 |
| I | Steady State + Developer Tool + Time-Saved Proof | 🔴 NOT STARTED | P3 | — |
| K | Marketing Division | 🔴 NOT STARTED | P3 | G1 (A+B+D must be green), G2, G3 |
| F | Ideas Division (optional) | ⚪ OPTIONAL | P3 | Once G+K exist |

| STAGE A Telegram + NLU + MA + Compliance Guardian + Silence | 🔴 NOT STARTED |
| --- | --- |

| Owner | Managing Agent + CEO (J) |
| --- | --- |
| Effort | ~5–8 days |
| Depends on | Ollama running, Python 3.10+ on Windows, BOT_TOKEN in .env |
| Priority | P0 — blocks everything |
| Loop stages | 01 GOAL → 03 APPROVE → 04 EXECUTE |
| Models | llama3.2:3b (NLU), llama3.1:8b (MA) |

- · Install python-telegram-bot (pip install python-telegram-bot). Store BOT_TOKEN in .env (git-ignored). No Docker, no broker. (R11)

- · Build NLU intake: llama3.2:3b parses plain-English CEO messages into structured Goal JSON.

- · Wire MA: llama3.1:8b receives Goal, routes to correct division, applies R1–R10 check.

- · Build Compliance Guardian: cross-cutting agent that vets every plan before Stage 04.

- · Implement R10 silence policy: MA does not speak unless decision pending, status changed, or 7 days elapsed.

- · Test: send 'check trading bot status' in Telegram → MA routes → division responds → report comes back.

| STAGE B Scheduler Verification & Self-Heal | 🔴 NOT STARTED |
| --- | --- |

| Owner | Managing Agent |
| --- | --- |
| Effort | ~2–3 days |
| Depends on | Stage A |
| Priority | P0 |
| Loop stages | 04 EXECUTE → 05 REPORT |
| Models | llama3.1:8b |

- · Verify heartbeat / HEARTBEAT.md scheduler is firing on correct intervals.

- · Add self-heal: if a scheduled job misses, MA detects and re-fires within 15 min.

- · Log all scheduler events to artifacts/scheduler_log.json.

- · Test: kill a scheduled task manually, verify MA detects and alerts within 15 min.

| STAGE C Sanitizer & Allowlist Remediation | 🔴 NOT STARTED |
| --- | --- |

| Owner | Developer Tool + CEO review |
| --- | --- |
| Effort | ~2–3 days |
| Depends on | Can run parallel with A/B |
| Priority | P1 (parallel) |
| Loop stages | 02 PLAN → 03 APPROVE → 04 EXECUTE |
| Models | qwen2.5-coder:7b (Developer Tool) |

- · Audit all tool calls: identify any external API calls, cloud references, or out-of-scope file writes.

- · Build sanitizer: strips any non-local model references from prompts before inference.

- · Build allowlist: only permitted tool paths and domains can be called by any agent.

- · CEO reviews diff of all changes before deploy (R8).

- · Test: attempt to call a disallowed endpoint → sanitizer blocks → MA logs → CEO alerted.

| STAGE D Operational Signals → GREEN | 🔴 NOT STARTED |
| --- | --- |

| Owner | Trading Division + Websites Division |
| --- | --- |
| Effort | ~3–5 days |
| Depends on | Stage A, Stage B |
| Priority | P1 — unblocks G1 |
| Loop stages | All six stages |
| Models | llama3.1:8b |

- · Fix Polymarket recency stale signal — update data feed or polling interval.

- · Fix Websites division brief freshness issue — ensure content signals current.

- · Both divisions must report GREEN status for two consecutive daily briefs.

- · MA confirms GREEN status to CEO. G1 unblocked once both are green.

- · Test: daily brief shows Trading=GREEN, Websites=GREEN for 2 days running.

| STAGE G Commercial Division ★ NEW / ENHANCED IN v5 | 🔴 NOT STARTED |
| --- | --- |

| Owner | Commercial Division (new) |
| --- | --- |
| Effort | ~5–7 days |
| Depends on | Stage A, Stage B; G2: one at a time |
| Priority | P1 |
| Loop stages | 02 PLAN → 03 APPROVE (Commercial scoring gate) |
| Models | llama3.1:8b + Python arithmetic tools |

- · Create Commercial division config and crew. Model: llama3.1:8b.

- · Implement Finance Reporting sub-function: daily PNL roll-up, weekly P&L statement.

- · Implement Business Case / Feasibility: go/no-go assessment template with all 5 KPI fields.

- · Implement ROI & Impact: scoring rubric, upside/effort/confidence fields, scenario modelling.

- · Implement Risk Monitoring: drawdown alert thresholds, cost spike detection.

- · Wire Commercial scoring gate: any new initiative must pass through Commercial before Board Pack.

- · All arithmetic via Python tools — never ask the LLM to calculate numbers.

- · Test: submit a test initiative → Commercial scores it → Board Pack blocked if score missing.

| STAGE E Research Division (on-demand first) | 🔴 NOT STARTED |
| --- | --- |

| Owner | Research Division |
| --- | --- |
| Effort | ~3–4 days |
| Depends on | Stage A; G2 |
| Priority | P2 |
| Loop stages | 01 GOAL → 05 REPORT |
| Models | llama3.1:8b + nomic-embed-text (opt-in semantic search later) |

- · On-demand first: CEO sends a research request → Research produces a brief → CEO reviews.

- · No autonomous periodic research until CEO explicitly enables it.

- · Build brief template: question, summary, sources, confidence, date.

- · Weekly opt-in: CEO can schedule a standing research brief topic via Telegram.

- · Test: send 'research the current state of Polymarket liquidity' → brief returned within session.

| STAGE H Holding Board v2 + Board Pack upgrade ★ NEW / ENHANCED IN v5 | 🔴 NOT STARTED |
| --- | --- |

| Owner | MA + CEO |
| --- | --- |
| Effort | ~3–4 days |
| Depends on | Stage G (Commercial scoring gate must be live) |
| Priority | P2 |
| Loop stages | 05 REPORT → 06 JUDGE |
| Models | llama3.1:8b |

- · Upgrade Board Pack to 8 required fields: Rationale, Upside, Effort, Confidence, Owner, Deadline, Dissent, Post-launch measurement.

- · MA blocks any decision missing a field from reaching CEO.

- · Wire Dissent Agent: for every proposed decision, a Critic agent must file at least one objection.

- · Weekly Board Pack digest: MA compiles all pending decisions into one Telegram message, CEO triage.

- · Test: propose a decision with a missing field → MA blocks it → MA messages CEO explaining what is missing.

| STAGE J Content Studio (light) ★ NEW / ENHANCED IN v5 | 🔴 NOT STARTED |
| --- | --- |

| Owner | Content Studio Division |
| --- | --- |
| Effort | ~4–5 days |
| Depends on | Stage D green (G1), Stage G; G2, G3, G4 |
| Priority | P2 |
| Loop stages | 02 PLAN (brief required) → 03 APPROVE → 04 EXECUTE (draft only) → 06 JUDGE |
| Models | llama3.1:8b |

- · Content Studio operates from approved briefs only — no open-ended content generation (G3).

- · Briefs must originate from CEO or from an approved Marketing campaign plan.

- · Content Studio may draft assets. All publishing escalates under R3 and R4 — CEO approval required (G4).

- · Light scope: social post drafts, website copy drafts, email drafts. No autonomous publishing.

- · New divisions obey silence policy R10 — no unsolicited output (G6).

- · Test: CEO provides a brief → Content Studio drafts → MA QAs → CEO reviews → CEO approves publish separately.

| STAGE I Steady State + Developer Tool + Time-Saved Proof | 🔴 NOT STARTED |
| --- | --- |

| Owner | All divisions + Developer Tool |
| --- | --- |
| Effort | ~4–6 days + ongoing |
| Depends on | Stages A–H, J stable |
| Priority | P3 |
| Loop stages | All stages |
| Models | llama3.1:8b (MA), qwen2.5-coder:7b (Developer Tool), nomic-embed-text (semantic search) |

- · Activate Developer Tool: qwen2.5-coder:7b, bounded to ai-capital-group/ folder only (R8).

- · CEO reviews and approves code diff via Telegram before any deploy.

- · Activate nomic-embed-text semantic memory for research and brief retrieval.

- · Time-Saved tracking active: CEO logs weekly hours saved vs baseline. R9 trigger monitored.

- · Two consecutive net-negative weeks → halt all new division rollout → review operating model (G7).

- · Test: Developer Tool generates a new reporting script → CEO sees diff in Telegram → approves → runs.

| STAGE K Marketing Division ★ NEW / ENHANCED IN v5 | 🔴 NOT STARTED |
| --- | --- |

| Owner | Marketing Division |
| --- | --- |
| Effort | ~5–7 days |
| Depends on | G1: A, B, D stable and green. G2. G3. Commercial Division active. |
| Priority | P3 — GATED |
| Loop stages | 02 PLAN (Commercial scores first) → 03 APPROVE → 04 EXECUTE → 06 JUDGE |
| Models | llama3.1:8b |

- · GATED: Marketing does not start until Stage A, Stage B, and Stage D are all stable and green (G1).

- · Commercial must score every proposed campaign before it reaches Stage 03 (G3).

- · Max 1 campaign decision per week (G3). Decision Queue cap still applies.

- · Marketing operates from approved campaign plans — no open-ended campaigns.

- · All external publishing escalates under R3 and R4 — CEO approval required.

- · Silence by default: Marketing only speaks when a decision is pending or status changes (G6).

- · Test: propose campaign → Commercial scores it → MA routes to CEO → CEO approves → Marketing executes → reports.

PLAN.md — Canonical Repo Reference

PLAN.md lives at ai-capital-group/PLAN.md and is the single source of truth for all work on this system. Any AI tool (CrewAI, Codex, Claude, or any future tool) must read PLAN.md completely before touching any code, config, prompt, or data.

What PLAN.md contains

- §1  System description and strategic intent

- §2  R1–R10 non-negotiable rules (in a table for fast reference)

- §3  Organisation structure — near-term and target org

- §4  The six-stage operating loop

- §5  Managing Agent role, authority, and escalation rules

- §6  Guardrails G1–G7

- §7  Model architecture (Ollama models only)

- §8  Board Pack requirements (8 fields)

- §9  Commercial Division Charter

- §10 Capability decisions (locked — do not re-open without CEO directive)

- §11 Stage plan and current status

- §12 File structure

- §13 Out of scope (Compliance Guardian blocks these)

- §14 How to use this document (for AI tools and for CEO)

Instructions for AI tools appear at the top of PLAN.md in a callout block: 'Read this file completely before touching any code, config, prompt, or data. Every rule here is non-negotiable unless a rule-change is explicitly recorded in section 10. If in doubt: stop, escalate to the Managing Agent, and wait.'

Infrastructure Already Live

| Phase | Component | Status | Notes |
| --- | --- | --- | --- |
| Phase 1 | Telemetry / Daily Brief | ✅ LIVE | daily_brief_latest.json generating |
| Phase 2 | Division Crews (crewai_hierarchical) | ✅ LIVE | trading=AMBER, websites=RED |
| Phase 3 | CEO / Holding Board (crewai_ceo) | ✅ LIVE | company_status=RED |
| Phase 3 | Latest commit | 67ec6c1 | All three phases confirmed |

Success Portrait

When this system is working as designed, a typical week looks like this:

- J opens Telegram. MA has queued 1–3 decisions needing approval — nothing else.

- J taps approve or reject on each. The loop closes or re-tasks.

- Daily briefs arrive at the scheduled time. J reads the summary, not the raw data.

- Commercial has scored any new initiative before it reached J. J only sees go/no-go with a number.

- Content Studio has a draft ready. J reviews it and approves publishing separately.

- Marketing fired one campaign this week. Commercial scored it first.

- The Time Saved sheet shows J saved 4–6 hours vs the baseline week.

- Two consecutive green weeks means the next stage can begin.

The CEO is in the loop for every consequential decision. The CEO is out of the loop for every routine one.

Companion Artifacts

| Artifact | Purpose |
| --- | --- |
| AI-Holding-Company_Operating-Model.png | Visual org chart — CEO → MA → 6 divisions, 6-stage loop, guardrails, escalation quick-ref |
| AI-Holding-Company_Goals-Decisions-Tracker.xlsx | Live tracker — Goals, Plans, Decisions Pending, Execution Log, Reports, Time Saved, Model Architecture, Guardrails |
| PLAN.md | Canonical tool-agnostic repo reference — read-first for any AI tool or agent |
| AI-Holding-Company_Sharpened-Project-Plan-v5.docx | This document — full v5 plan with all stages, rules, and charters |

AI Holding Company  ·  v5  ·  2026-04-13  ·  100% local · Ollama / python-telegram-bot / CrewAI  ·  PLAN.md §14